## HR REVIEW
HR REVIEW
PHASE 1 | ITEM | AUGUST 2024
|  | TIMESOFT FEATURES/PRACTICE | HRMS FEATURES/PRACTICE | HR ANALYSIS |  |  | PROGRAMMER ACTION
|  |  |  | PROBLEM FIND |  | REMARK | ACTION PLAN |  | PERSON IN-CHARGE |  | STATUS | REMARK
|  |  |  | HRMS | MOBILE APPS |  | HRMS | MOBILE APPS | HRMS | MOBILE APPS
| GENERAL SETTING (MASTER) | MANUAL -> (TIMESOFT SETTING) 1. company setting 2. division 3. department 4. section 5. cost centre 6. job grade 7. occupation 8. sex 9. race 10. country 11. state, city, 12. working days 13. working hours 14. daily rate base 15. npl rate base 16. ot rate base 17. retired age 18. retired date 19. public holiday 20. bank type 21. leave scheme 22. benefit scheme 23. EPF class 24. SOCSO class 25. EIS class 26. TAX rate 27. HRDF rate 28. Resigned Setting (Staff Encashment & Pro Rate Formula) | MANUAL -> (MASTER DATA) 1. division 2. department 3. section 4. job grade 5. occupation 6. sex 7. race 8. country 9. state, city, 9. bank type 10. company setting (just have basic information only) 12. working days 13. working hours 14. daily rate base 15. npl rate base 16. ot rate base 17. leave scheme 18. benefit scheme 19. public holiday (leave setting) | NEED TO ADD ON (PENDING) 1. cost centre (to seperate cost by BU) 2. retired age (in order to determine social security retirement benefit) 3. retired date (to monitor staff when them retired) 4. EPF class (have 5 different table of contribution rate based on criteria of staff) : refer to HR remark 5. SOCSO class (have 5 different table of contribution rate based on criteria of staff) : refer to HR remark 6. EIS class (have 2 type of contribution rate based on criteria of staff) : refer to HR remark 7. HRDF (company need contribute 1% per head of staff) 8. Tax Rate (calculation) : refer to HR remark 6. EIS c 9. Company Setting (Stautory details) : refer to HR remark 10. Resigned Setting (Staff Encashment & Pro Rate Formula) |  | 9. Company Setting (Stautory details) : -
EMPLOYEE PROFILE:
| PERSONAL PROFILE | MANUAL (KEY-IN/select) 1. picture 2. employee ID 3. name 4. hired date (calendar select) 5. birth date (calendar select) 6. NRIC 7. basic salary 8. sex (selected) 9. race (selected) 10. nationality (selected) 11. passport 12. job grade (selected) 13. working days (selected) 14. working hours (selected) 15. daily rate base (selected) 16. npl rate base (selected) 17. ot rate base (selected) 18. leave scheme (selected) 19. benefit scheme (selected) 20. division (selected) 21. department (selected) 22. section (selected) 23. cost centre (selected) 24. address 25. email 26. probation period (calendar select) 27. telephone number select) 28. user creation (TAS) | MANUAL (KEY-IN/select) - 1. picture 2. employee ID 3. name 4. hired date (calendar select) 5. birth date (calendar select) 6. NRIC 7. marital status 8. sex (selected) 9. race (selected) 10. nationality (selected) 11. passport 12. employee type 13. address 14. probation period 15. email 16. telephone number 17. spouse working (tick) 18. children in university 19. children under 18 20. basic salary 21. bank account 22. bank type (selected) 23. EPF account 24. payment mode 25. allowance 26. department (selected) 27. section (selected) 28. occupation (selected) 29. division (selected) 30. job grade 31. user creation | Refer to the current practice required details (we already highlited the important details that required) | VIEW ONLY
| ALLOWANCE/DEDUCTION | MANUAL -> (key-in) 1. attendance allowance 2. transport allowance 3. telephone allowance 4. person in-charge allowance 5. loan deduction 6. cp38 deduction 7. skkpa deduction 8. hostel utilities deduction | MANUAL (key-in) -> PAYMENT INFORMATION (ALLOWANCE) 1. attendance allowance 2. transport allowance 3. telephone allowance 4. person in-charge allowance | NEED TO ADD ON (PENDING) TYPE OF DEDUCTION CODE, CURRENTLY ONLY HAVE COLUMN FOR ALLOWANCE | VIEW ONLY
| INCOME TAX INFORMATION | MANUAL -> (key-in) 1. income tax account 2. marital status 3. dependent children relief 4. working spouse 5. CP8D employee status | - | PENDING | VIEW ONLY
| GOVERNMENT CONTRIBUTION DETAILS | MANUAL -> (key-in/select) 1. EPF class (selected) 2. EPF account 3. SOCSO class (selected) 4. SOCSO account & SSFW 5. EIS class (selected) 6. HRDF (selected) | MANUAL (key-in) -> 1. EPF account | PENDING | VIEW ONLY
| BANK DETAILS | MANUAL -> (key-in/select) 1. bank (type) (selected) 2. bank account | MANUAL -> (key-in/select) 1. bank (type) (selected) 2. bank account | √ | VIEW ONLY
| F0REIGN WORKER DETAILS | MANUAL -> (key-in) 1. work permit/employe pass no. 2. arrival date 3. issue date 4. expired date 5. valid period | - | PENDING | VIEW ONLY
ATTENDANCE:
| CLOCK IN/OUT | MANUAL -> CAPTURE ONCE IMPORT TXT FILE FROM CURRENT MACHINE | AUTO -> CAPTURE FROM HIK MACHINE | PENDING | VIEW ONLY | currently still using old thumbprint machine, because we still using timesoft to process payroll. ellyana already test to import txt file from new machine into TAS but have data not accured with old thumbprint machine.
| PUBLIC HOLIDAY | AUTO -> CAPTURE FROM TIMESOFT SYSTEM (LEAVE SETUP) | AUTO -> CAPTURE FROM HRMS (LEAVE) | √ | VIEW ONLY | -
| LEAVE RECORD | AUTO -> CAPTURE FROM TIMESOFT SYSTEM (LEAVE RECORD) | AUTO -> CAPTURE FROM MOBILE APPS & WEBSITE APPLICATION | PENDING | PENDING | STAFF CANNOT USE YET. ONLY HAVE 1 APPROVAL.
| OT RECORD | AUTO -> CALCULATE BASED ON THUMBPRINT RECORD | AUTO -> CAPTURE FROM MOBILE APPS & WEBSITE APPLICATION | PENDING | PENDING | STAFF CANNOT USE YET. ONLY HAVE 1 APPROVAL.
LEAVE:
| LEAVE APPLICATION | STAFF APPLY IN ERP SYSTEM | STAFF APPLY MOBILE APPS & HRMS WEBSITE | PENDING | PENDING -> TYPE OF LEAVE (+) - GATEPASS LEAVE REASON (+) -SPECIAL LEAVE - FESTIVAL SEASON - TRANSPORTATION ISSUE - NATURAL PHENOMENON - GATEPASS APPLICATION - FAMILY MATTER - OTHERS | STAFF CANNOT USE YET. ONLY HAVE 1 APPROVAL.
| LEAVE APPROVAL | MANUAL -> ERP SYSTEM ->MANUAL KEY-IN INTO TIMESOFT -> APPROVE IN ERP TAS | AUTO -> CAPTURE FROM MOBILE APPS & WEBSITE APPLICATION -> APPROVE IN HRMS | PENDING | PENDING | STAFF CANNOT USE YET. ONLY HAVE 1 APPROVAL.
OVERTIME:
| OT APPLICATION | STAFF APPLY IN ERP SYSTEM | STAFF APPLY MOBILE APPS & HRMS WEBSITE | PENDING | PENDING | STAFF CANNOT USE YET. ONLY HAVE 1 APPROVAL.
| OT APPROVAL | MANUAL -> ERP SYSTEM -> APPROVE IN TAS | AUTO -> CAPTURE FROM MOBILE APPS & WEBSITE APPLICATION -> APPROVE IN HRMS | PENDING | PENDING | STAFF CANNOT USE YET. ONLY HAVE 1 APPROVAL.
SHIFT PATTERN
| SHIFT CODE | AUTO ->CAPTURE FROM TAS SETTING (SHIFT LINGKAGE) | AUTO ->CAPTURE FROM HRMS (SHIFT) | √ | VIEW ONLY | -
PHASE 2 | PAYROLL TRANSACTION
| PAYSLIP | MANUAL -> SENT TO STAFF THROUGH WHATSAPP (GENERATE FROM TIMESOFT SYSTEM) | - | PENDING | PENDING | -
| TEXT FILE | AUTO -> GENERATE FROM TIMESOFT SYSTEM | - | - |  | -
PAYROLL REPORT
| SUMMARY REPORT | AUTO ->GENERATE FROM TIMESOFT SYSTEM | - | - |  | -
| DETAIL REPORT | AUTO -> GENERATE FROM TIMESOFT SYSTEM | - | - |  | -
GOVERNMENT CONTRIBUTION TRANSACTION
| KWSP | AUTO ->GENERATE TXT FILE FROM TIMESOFT SYSTEM | - | - |  | -
| SOCSO/EIS | AUTO ->GENERATE TXT FILE FROM TIMESOFT SYSTEM | - | - |  | -
| HRDF | AUTO ->GENERATE TXT FILE FROM TIMESOFT SYSTEM | - | - |  | -
| TAX | AUTO ->GENERATE TXT FILE FROM TIMESOFT SYSTEM | - | - |  | -
Note on B18: Iwana (2024-08-22 12:21:17) 1. CLOCK-IN 2. LUNCH IN 3. LUNCH-OUT 4. CLOCK-OUT